## Product
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned
1 | Home Page | Common | Medium | Show sliders, hot posts, latest courses + the right sider with the course search box & five featured courses (thumbnail, title) - Slider information: image, title; the user is redirected to the slider's backlink on his/her clicking - Post information: thumbnail, title, category; the user is redirected to the Blog Details page on his/her clicking - Course information: thumbnail, title, list price, sale price; the user is redirected to the Goods Details page on his/her clicking | Interation1
2 | User Login | Common | Simple | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Interation1
3 | User Logout | Common | Simple | When user click Logout, user is redirected to the login page | Interation1
4 | User Register | Common | Simple | This is a pop-up screen which allows the user to register to the system by inputing following information: full name, user title (Mr, Mrs, Ms,..), email, mobile, address; User then needs to verify by clicking the link sent via email to him/her before being able to access the system | Interation1
5 | Reset Password | Common | Medium | The user to input his/her email to receive the reset password link - On clicking the link, the user is redirected to the page in which s/he input new password (twice) - Note that the link is only available for a specific time duration as configured in the system config file. | Interation1
6 | User Authorization | Common | Medium | This is authorization mechanism in the system, including the specify the user's role, his/her authorized page links (building the displayed menu items and preventing unauthorized access via enter the links directly). The scope of this function also includes building the header, footer, the main function menu (for both Admin and NonAdmin parts) | Interation1
7 | Update First Profile | Common | Simple | This is a pop-up screen which allows the user to insert his/her first profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Interation1
8 | News List | Public | Medium | Show the news paginatedly (sorted by updated date) + the right sider with the post search box, post categories, five featured posts (thumbnail, title); Post information includes its thumbnail, title, category, post date, brief-info; the user is redirected to the News Details page on his/her clicking on a post, redirected to this News List page if the user clicks on a post category | Interation2
9 | News Details | Public | Simple | Show news details (including title, author, updated date, brief info, and post content) + the right sider with the post search box, post categories, five featured posts (thumbnail, title). The News List page is shown when the user clicks on a post category | Interation2
10 | Search News | Public | Medium | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status; also the user can search the post by title - The list can be sortable by title, category, author, featured, or status | Interation3
12 | Tutorial | Public | Simple | Show the tutorial page that people can see how and what to do in Covid time | Interation2
12 | Profile Details | User | Simple | After fill out the application, user can read their information | Interation1
13 | Update Profile | User | Simple | User can update their information in order that the information is correct | Interation2
14 | List User | Admin | Simple | Show list of user who participate in this system | Interation2
15 | Manage News | Admin | Simple | Use API to get what users input for their news and then the server to manage new news in the database based on that information | Interation2
16 | Manager Account | Admin | Simple | Admin can see Account Details and manage it | Interation2
17 | Messenger | Common | Complex | When a patient clicks on the messenger button on their homepage, they can chat with the hospital that is responsible for taking care of them. In other way, the hospital can access to another Messenger screen that allows them to see all the patients that are currently taking care of | Interation3
18 | Create Timetable | User | Medium | Use API to get what users input for their tasks and then the server creates new tasks in the database based on that information | Interation2
19 | Timetable Details | User | Medium | Retrieve all information about the tasks from the database and put them to the website by using API | Interation3
20 | Update Timetable | User | Medium | Change the information of a tasks on the website and send the id to the server through an API, after that the server updates new information in the database. The new change will be displayed on the screen | Interation3
21 | Delete Timetable | User | Medium | Delete the tasks by providing the id to the server through an API, the server uses the id to delete the right tasks in the database. After deleting the news, display the task list on the screen | Interation3
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Feature | Level* | In Charge | Status | Notes
1 | Design Front-end | Common | Medium | Hoàng Việt Hùng | Done
2 | Design Front-end | Common | Medium | Vũ Minh Quang | Done
3 | User Login | Common | Simple | Nguyễn Văn Mạnh | Done
4 | User Logout | Common | Simple | Lê Đức Chính | Done
5 | User Register | Common | Simple | Nguyễn Văn Mạnh | Done
6 | User Authorization | Common | Simple | Nguyễn Văn Mạnh | Done
7 | Update First Profile | Public | Simple | Lê Đức Chính | Done
8 | Profile Details | Public | Simple | Lê Đức Chính | Done

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Feature | Level* | In Charge | Status | Notes
1 | Turtorial | Common | Simple | Hoàng Việt Hùng | Done
2 | List News | Common | Simple | Vũ Minh Quang | Done
3 | List Account | Common | Simple | Hoàng Việt Hùng | Done
4 | News Details | Common | Simple | Vũ Minh Quang | Done
5 | Ban Account | Admin | Simple | Hoàng Việt Hùng | Done
6 | Edit Account | Admin | Simple | Nguyễn Văn Mạnh | Done
7 | Create News | Admin | Medium | Nguyễn Văn Mạnh | Done
8 | Time Table | Common | Medium | Lê Đức Chính | Done

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Feature | Level* | In Charge | Status | Notes
1 | Reset PassWord | Common | Simple | Nguyễn Văn Mạnh | Done
2 | Create Time Table | Hospital | Medium | Lê Đức Chính | Done
3 | Create Time Table | User | Medium | Lê Đức Chính | Done
4 | Show List News | Admin | Simple | Hoàng Việt Hùng | Done
5 | Update News | Admin | Simple | Nguyễn Văn Mạnh | Done
6 | View News | Admin | Simple | Hoàng Việt Hùng | Done
7 | Hide News | Admin | Simple | Vũ Minh Quang | Done
8 | Search News | Common | Simple | Vũ Minh Quang | Done
8 | Categories News | Admin | Simple | Nguyễn Văn Mạnh | Done
9 | Messenger | Common | Complex | Lê Đức Chính | Done